# Senatla Ops GitHub Delivery Backlog

Repository audit, project board controls, and implementation-ready work

Updated 31 October 2026

Purpose. This report converts the repository audit into an accountable delivery plan. Broad issues remain outcome epics; the new tasks define smaller work boundaries with acceptance criteria, dependencies, estimates, ownership, milestones, and board fields.

Current conclusion. The immediate release risk is governance and proof, not a lack of feature ideas. The next work should align the release branches, prove hosted configuration, complete persisted operational boundaries, and then run cross-role UAT.

# Contents

1 Current delivery state

2 Delivery roadmap

3 Implementation ready tasks

4 Critical execution sequence

5 Definition of done

6 Commercial viability review

7 Three pass review

# 1 Current delivery state

| Issues organized | New tasks | Milestones | Accountable owner |
| --- | --- | --- | --- |
| 29 | 12 | 5 | OhhttooeXCIV |

Every repository issue is assigned to OhhttooeXCIV; the existing collaborator remains on issues 19 and 20.

Issues 4 through 20 and tasks 86 through 97 are on the Senatla Ops project board.

Corrected Target Date, Delivery Stage, Risk Category, and Client Decision fields are available.

Pull request 82 is classified as P0 Security work in Code Review.

# 2 Delivery roadmap

| Milestone | Purpose | Exit evidence |
| --- | --- | --- |
| M0 Governance and Access | Branch rules, identity, data boundaries, deployment access, and client decisions | Protected release path, access proof, negative tests, and recorded decisions |
| M1 Operational Foundations | Site-day, workforce, recovery, private evidence, and document controls | Persisted workflows, recovery proof, audit history, and reproducible artifacts |
| M2 Controlled Pilot | Assets, inspections, maintenance, and source-backed analytics | Clean import, safety blocks, independent approvals, and reconciled metrics |
| M3 UAT and Release | Role journeys, recovery rehearsal, production mapping, and acceptance | Desktop and mobile proof, restore rehearsal, rollback target, and sign-off |
| M4 Reuse and Scale | Reusable architecture and delivery workflows | Domain-neutral packages, consumer proof, and adoption guidance |

# 3 Implementation ready tasks

| Issue | Priority | Task | Estimate | Stage |
| --- | --- | --- | --- | --- |
| 86 | P1 | Persist the complete site day record | 3 to 5 days | M1 |
| 87 | P0 | Make dev the integration default and protect main releases | 0.5 to 1 day | M0 |
| 88 | P0 | Verify hosted runtime configuration and preview smoke tests | 1 to 2 days | M0 |
| 89 | P1 | Enforce ownership SLA and immutable issue history | 3 to 4 days | M1 |
| 90 | P1 | Convert failed inspections into defects and safety blocks | 5 to 8 days | M2 |
| 91 | P1 | Stage asset CSV imports before writes | 4 to 6 days | M2 |
| 92 | P1 | Replace unsupported executive claims | 3 to 5 days | M2 |
| 93 | P1 | Enforce independent return to service approval | 2 to 4 days | M2 |
| 94 | P1 | Move operational evidence into private storage | 4 to 6 days | M1 |
| 95 | P2 | Generate and verify approved documents with one command | 3 to 5 days | M1 |
| 96 | P0 | Add release journeys for every operational role | 4 to 7 days | M3 |
| 97 | P1 | Publish a reusable application quality workflow | 2 to 4 days | M4 |

## Issue 86 Persist the complete site day record

Priority P1  |  Parent epic 10  |  M1 Operational Foundations  |  Estimate 3 to 5 days

Persist work plan, location, trips, safety, attendance, signature reference, and delivery result in one versioned payload.

Reuse the existing idempotency key and queue so retries cannot duplicate attendance or trip records.

Reject incomplete context and sites outside the actor's permitted scope.

Prove online, retryable, and accepted outcomes on desktop and at 390 px.

GitHub issue: https://github.com/Sankofa-Digital-Studio/senatla-ops-internal-automation-solution/issues/86

## Issue 87 Make dev the integration default and protect main releases

Priority P0  |  Parent epic 4  |  M0 Governance and Access  |  Estimate 0.5 to 1 day

Set dev as the default branch and require pull requests for protected branches.

Require the agreed application, database, responsive, and native checks.

Require CODEOWNER approval for main and prevent force pushes and deletion.

Prove the rules with a test release pull request and align contributor documentation.

GitHub issue: https://github.com/Sankofa-Digital-Studio/senatla-ops-internal-automation-solution/issues/87

## Issue 88 Verify hosted runtime configuration and preview smoke tests

Priority P0  |  Parent epic 7  |  M0 Governance and Access  |  Estimate 1 to 2 days

Confirm Vercel team, project, and branch ownership without recording secrets.

Fail hosted builds when required public Supabase configuration is missing.

Prove login, one protected route, and unauthenticated redirection against an exact commit.

Record the current deployment, environment, responsible owner, and rollback target.

GitHub issue: https://github.com/Sankofa-Digital-Studio/senatla-ops-internal-automation-solution/issues/88

## Issue 89 Enforce ownership SLA and immutable issue history

Priority P1  |  Parent epic 11  |  M1 Operational Foundations  |  Estimate 3 to 4 days

Replace mutable audit JSON with append-only issue events.

Enforce valid statuses, transitions, owners, due dates, and organization and site access.

Prevent clients from changing or deleting history.

Cover creation, escalation, resolution, and prohibited changes in UI and pgTAP tests.

GitHub issue: https://github.com/Sankofa-Digital-Studio/senatla-ops-internal-automation-solution/issues/89

## Issue 90 Convert failed inspections into defects and safety blocks

Priority P1  |  Parent epic 13  |  M2 Controlled Pilot  |  Estimate 5 to 8 days

Add versioned inspection templates, runs, answers, defects, and safety blocks.

Create a defect and work order atomically when a critical item fails.

Prevent blocked assets from assignment or return to service.

Prove mobile capture, retry safety, and authorization with pgTAP and 390 px tests.

GitHub issue: https://github.com/Sankofa-Digital-Studio/senatla-ops-internal-automation-solution/issues/90

## Issue 91 Stage asset CSV imports before writes

Priority P1  |  Parent epic 12  |  M2 Controlled Pilot  |  Estimate 4 to 6 days

Provide a versioned template and dry run with no writes.

Report missing identifiers, duplicates, stored conflicts, invalid links, and invalid custodians or sites.

Apply only an explicitly approved clean import in one transaction.

Prove case-insensitive identity, cycle prevention, audit history, and idempotent re-import.

GitHub issue: https://github.com/Sankofa-Digital-Studio/senatla-ops-internal-automation-solution/issues/91

## Issue 92 Replace unsupported executive claims

Priority P1  |  Parent epic 14  |  M2 Controlled Pilot  |  Estimate 3 to 5 days

Define source, period, unit, numerator, denominator, and calculation version for every metric.

Remove hard-coded success claims and distinguish actual, target, provisional, stale, and missing values.

Provide drill-down to contributing source records.

Reconcile empty, partial, duplicate, provisional, and complete fixtures in integer minor units.

GitHub issue: https://github.com/Sankofa-Digital-Studio/senatla-ops-internal-automation-solution/issues/92

## Issue 93 Enforce independent return to service approval

Priority P1  |  Parent epic 13  |  M2 Controlled Pilot  |  Estimate 2 to 4 days

Move blocker checks and activation into a restricted database function.

Reject self-approval, wrong-role access, stale requests, and unresolved safety or maintenance blockers.

Make approval and activation one atomic transaction.

Record the decision and asset state transition in immutable audit events.

GitHub issue: https://github.com/Sankofa-Digital-Studio/senatla-ops-internal-automation-solution/issues/93

## Issue 94 Move operational evidence into private storage

Priority P1  |  Parent epic 15  |  M1 Operational Foundations  |  Estimate 4 to 6 days

Replace base64 and typed paths with private object references and controlled metadata.

Authorize short-lived access through role and site checks.

Retain hash, content type, size, actor, source record, and retention status.

Prove cross-site denial, retry idempotency, and safe orphan cleanup without leaking paths.

GitHub issue: https://github.com/Sankofa-Digital-Studio/senatla-ops-internal-automation-solution/issues/94

## Issue 95 Generate and verify approved documents with one command

Priority P2  |  Parent epic 16  |  M1 Operational Foundations  |  Estimate 3 to 5 days

Add an artifact manifest and one documented generation command.

Fail on missing output, render failure, broken link, version mismatch, or prohibited sensitive patterns.

Produce no source-controlled difference on a second run.

Separate approved, internal, and superseded artifacts and retain a compact CI failure report.

GitHub issue: https://github.com/Sankofa-Digital-Studio/senatla-ops-internal-automation-solution/issues/95

## Issue 96 Add release journeys for every operational role

Priority P0  |  Parent epic 17  |  M3 UAT and Release  |  Estimate 4 to 7 days

Cover Site Manager, Office Administrator, Director, and read-only critical journeys on desktop and at 390 px.

Verify direct-route and control denial for unauthorized roles.

Retain screenshot, trace, route, role, viewport, and commit SHA on failure.

Use approved fixtures without client personal data and link evidence from the release checklist.

GitHub issue: https://github.com/Sankofa-Digital-Studio/senatla-ops-internal-automation-solution/issues/96

## Issue 97 Publish a reusable application quality workflow

Priority P1  |  Parent epic 20  |  M4 Reuse and Scale  |  Estimate 2 to 4 days

Extract pinned Node, package, Supabase, browser, permission, timeout, and artifact controls behind workflow inputs.

Keep project-specific commands configurable and cache by compatible lockfile.

Prove Senatla Ops can consume the workflow without weakening its current gate.

Validate a second consumer example and publish an adoption checklist.

GitHub issue: https://github.com/Sankofa-Digital-Studio/senatla-ops-internal-automation-solution/issues/97

# 4 Critical execution sequence

Complete issue 87 so new work targets dev and main remains a reviewed production branch.

Resolve issue 88 to prove hosted runtime configuration and controlled QA access.

Complete issues 86, 89, 94, and 95 as the operational foundation.

Complete issues 90, 91, 92, and 93 for the controlled pilot.

Run issue 96 after the dependent role workflows are stable.

Complete issue 97 after the Senatla-specific gate is stable enough to extract without weakening it.

# 5 Definition of done

A focused pull request links to the issue and demonstrates the acceptance criteria.

New mutations create required audit evidence and authorization changes include negative tests.

Rendered changes have desktop and 390 px proof against the reviewed commit.

Schema changes have clean reset and database-contract evidence.

Deployment changes record the approved commit, environment, current deployment, and rollback target.

Durable documents avoid stale immutable preview URLs and the public Senatla Trading website remains untouched.

# 6 Commercial viability review

MaintainX, Fleetio, and HCSS Equipment360 already provide mature work-order, fleet, and equipment-maintenance capabilities. Senatla Ops should not reproduce a broad CMMS or fleet suite.

Its viable boundary is a source-linked operational record for one operating company. People, safety, attendance, payroll control, site synchronization, assets, maintenance, maker-checker decisions, and audit evidence share one authorization and audit model. The differentiator is the explainable operational heartbeat: each outcome can be traced to an actor, site, time, approval, and source record.

MaintainX work order management: https://www.getmaintainx.com/use-cases/work-order-management

Fleetio asset management: https://www.fleetio.com/features/asset-management-software

HCSS Equipment360: https://www.hcss.com/equipment360/what-is-equipment360/

# 7 Three pass review

## Pass 1 Repository gaps

The initial scan found broad epics, incomplete board coverage, inconsistent repository metadata, narrow cross-role browser proof, and unfinished persistence boundaries for site-day, inspection, evidence, and reporting workflows.

## Pass 2 Duplication challenge

Authentication, negative RLS contracts, deterministic verification, attendance retry, readiness confirmation, and parts of the offline outbox already exist. New issues for those features would duplicate closed or active work.

## Pass 3 Reconciled backlog

The final tasks target observable remaining boundaries: live GitHub configuration, hosted deployment proof, missing persisted fields, immutable history, controlled import, inspection and safety-block contracts, database-enforced return approval, private evidence, source-backed metrics, reproducible documents, cross-role UAT, and reusable CI.